## Slide 1: Learning Management Systems
Transition to Canvas
Steering Committee
May 13, 2019

## Slide 2: Agenda
Current Moodle migration status
Migration considerations
SHP migration plans
Course inventory
Migration estimations (by LMS and by course type)
Work groups – LMS Support
Data retention/course archive
Unizin Summit
Canvas Transition Site
Open forum

## Slide 3: RBHS Migration Progress
School / Unit | Term | #Courses | Kickoff | Inventory | Migration | White-glove | Completed
Biopharma Educational Initiative | All | 84 | X | X | 90% | 75% | 7/2019
Rutgers School of Dental Medicine (RSDM) | All | ? | X | X | ?% | N/A | 7/2019 - ?%
School of Graduate Studies (SGS) | All | 130 | X | X | 100% | N/A | N/A
School of Health Professions (SHP) | SP2020 | 171 | X | X | 25% | 10% | 11/2019 - 0%
New Jersey Medical School (NJMS) | N/A | N/A | X | N/A |  |  | 
School of Nursing | N/A | N/A | X | X | 100% | N/A | N/A
School of Public Health (SPH) | N/A | N/A | X | X | 100% | N/A | N/A
Robert Wood Johnson Medical School | N/A | N/A | X | N/A | 100% | N/A | N/A

## Slide 4: Migration Considerations
Suggestions from last SC Meeting:
Standardized communications between migration teams, schools and faculty
Coordination and direction from school, unit or program directors on migration scope
Flexibility and focus on setting migration priorities established by school
Handle but not encourage individual migration requests, funnel through school migration coordinator
Added Will Pagan, Director of Instructional Design, TLT to SC

## Slide 5: SHP Migration Plans
Target: Term Spring 2020; 171 courses; November 2019
Organized and prioritized by program
Course tracking and faculty coordination provided by SHP in conjunction with TLT
Major checkpoints established:
  Prioritized program and course inventory
  Timeline and assigned resources
  Migration of courses
  Handoff from TLT to faculty
    Course content will be transferred to Canvas Template
    ID has completed a verification of content transferred
    ID has created an "exception" list of items that an Instructor needs to review for completeness and accuracy
    ID provides suggestions for improvement that an Instructor to consider
    An invitation for consultation on course improvement
  Faculty or Program approval and signoff on course acceptance for content and teachability
Notes: On this slide I want to emphasize the effort and dialog we have had with SHP. Given the variety of starting points within RBHS (Some schools complete, SHP had yet to do much at all), the process for SHP has been from the ground up and could be viewed as a model for other units moving forward.

## Slide 6: Course Inventory by LMS
Chart: LMS Landscape – Past 2 Academic Years
| Sakai | Blackboard | Moodle | eCollege | Canvas
Sales | 0.48 | 0.16 | 0.08 | 0.02 | 0.26
Chart: LMS Landscape – Spring 2019
| Sakai | Blackboard | Moodle | eCollege | Canvas
Courses | 3503 | 765 | 447 | 0 | 3051

## Slide 7: Moodle migration estimates
Tier 1 = 1 day to complete
Tier 2 = 2-5 days to complete
Tier 3 = up to 2 weeks
Large course files have frozen the system during migration and requires a second round.
News Forum is lost during migration and needs to be copy & pasted manually.
Certain quiz questions do not migrate over, but some of them can be recreated with Quiz.next. More interactive questions are lost.
Moodle games cannot be migrated over, but maybe recreated with an external tool if available.
Question banks default to store questions on the course level, not user level.
Question bank organization can be problematic and require additional manual effort.
Moodle Tool | Tier 1 | Tier 2 | Tier 3
Assignments | X |  | 
Linked Content |  | X | 
Discussion & PMs |  | X | 
Sections |  |  | X
Forums |  | X | 
Gradebook |  | X | 
Kaltura Videos |  |  | X
Meetings Recordings |  | X | 
Private Files Repositories | X |  | 
Syllabus | X |  | 
Quizzes |  | X | 
Question Banks |  |  | X
Wiki |  |  | X
SCORM |  |  | X
News Forum |  | X | 
Mail |  |  | X

## Slide 8: Sakai migration estimates
Tier 1 = 1 day to complete
Tier 2 = 2-5 days to complete
Tier 3 = up to 2 weeks
Preliminary estimates to be refined during migrations with review of existing courses
All estimates are "worst case", as some modules may be implemented with default values or not fully employed
Sakai Tool | Tier 1 | Tier 2 | Tier 3
Announcements |  | X | 
Assignments | X |  | 
Deep Linked Content |  | X | 
Discussion & Pvt Messages |  | X | 
Lessons |  |  | X
Forums | X |  | 
Forums (multiple) |  | X | 
Gradebook Gradebook 2 |  | X | 
Kaltura Videos |  |  | X
Meetings Recordings |  | X | 
Postem |  | X | 
Resources |  | X | 
Syllabus | X |  | 
Tests & Quizzes |  | X | 
Question Pools |  |  | X
Wiki |  |  | X
VoiceThread | X |  | 
VoiceThread Assignment |  |  | X
SCORM |  | X | 

## Slide 9: Working Groups
Topic/Issue | Deliverable/Expectation | Group Assigned | Chair | Cadence
Guidelines on Use of LMS | · Guiding Principles for LMS course Implementation · Use case mapping of “course” types to be implemented in LMS/Canvas · Definitions / Glossary | Faculty Advisory | LMS Project | Weekly 1 hour sessions for 1 month
Non-Instructional Project Sites Use Cases | · Use case matrix/mapping of solutions · Definitions / Glossary | Faculty Advisory | LMS Project | Weekly 1 hour sessions for 1 month
Course Provisioning | · Allowable methods (pros/cons) · Administrative requirements / controls · Service level requirements / objectives | Faculty Advisory | LMS Project | Weekly 1 hour sessions for 1 month
Best Practices on Canvas Course Development | · Canvas Feature/Function awareness training · Sample course discussion / dissection · Instructional Design approach · Migration lessons | Instructional Technology | TLT | Ongoing – bi-weekly(?)
LMS Support (e.g. Service Desk) | · Process development / optimization · Knowledge Management / Development · Service Desk expectation · Service Level requirements | ? (Service Management / OIT) Faculty Instructional | OIT | Monthly

## Slide 10: LMS Support – Working Group
Existing LMS and OIT Support teams convened to discuss current state of support
  Multiple support teams, processes, contact points and service levels
  Recent incidents uncovered required improvements in processes, tools and coordination
Identified Critical Success Factors (Migration and Final State)
  A single point of contact for all LMS incidents and support calls
  Improve internal coordination between support groups
  Establish and share knowledge between support groups and end-users
  Improve communications to faculty and end-users for outages, changes and other notifications
  Migrate and position support to leverage Rutgers IT Service Management initiatives

## Slide 11: Data Retention/Content Archive
University Policy to archive course content and student interaction data for a period after course completion; retention period varies across the university
Accreditation audits require access to courses and student learning experience
Evidence for a response to student grade disputes or changes
Courses are sometimes not taught for a few years, so content needs to be available when required

## Slide 12: Unizin Summit
Consortium working groups and committees
Unizin learning technologies
Canvas roadmap
Learning analytics (UDP)
Transition to Canvas
  Discussions with Michigan, Minnesota, and Indiana
  Discussion with Instructure regarding migration tool
  Gaining faculty buy-in

## Slide 13: Canvas Transition Site Update
Steering Committee Page
  Membership
  Meeting minutes/summaries/slide decks
  Question/feedback form
Working Groups Page
  Descriptions and anticipated deliverables
  Meeting minutes/summaries/slide decks
  Feedback form
  Get involved (participation request)
Transition Progress
  Status reports
  Progress tracking > Transition Dashboard
  Project timelines
Notes: https://test-ru-canvas.pantheonsite.io/transition/steering-committee/

## Slide 14: Next Steps
Complete preliminary inventory of existing LMS courses
Verify target completion dates for Moodle migration
Develop progress tracking system / status reporting
Preliminary planning meeting with Blackboard stakeholders
Continue to engage Instructure and vendors regarding Sakai migration tool/services
Develop data retention/content archive plans for each LMS
Provide University community with project update
Initiate discussion on course fee structure and funding model

## Slide 15: Appendix

## Slide 16: Key Project Risks and Issues
Risk / Issue | Impact | Plan
Need of guidelines on use of LMS for non-academic scenarios | The need of established guidelines on the use of LMS for non-academic student use cases (demographically based sites, student groups, etc.)​ could negatively impact the student experience The need of guidelines creates risks around what new solutions will or won't be needed for non-instructional project sites. | Establish a Committee comprised of Faculty, Staff, Stakeholders and IT to develop guidelines and policies on the use of LMS
Need of Project Sites Solution | Approx 25,000 project sites are on Sakai. | Users can continue to utilize legacy LMSs for non-academic use until further notice. A use case matrix is in development to identify solutions for projects sites. Steering Committee and Project Teams will work to fill gaps via development or procurement of new solutions.
A streamlined help desk support model would improve customer experience. | Current help desk process is a direct handoff from OIT help desk to the LMS help desk | A coordinated optimization effort should be initiated with the Rutgers Service Management Office and the two help desks.

## Slide 17: Key Project Risks and Issues
Risk / Issue | Impact | Plan
Sakai GradeBook passback functionality to Rutgers SIS is not available in Canvas | The lack of GradeBook passback functionality in Canvas would require a manual workaround | A development effort has been identified to provide the necessary functionality in Canvas, however, target date for completion is 4Q19. Thus Sakai migrations will be deferred until available.
Sakai migration pathways are typically inefficient | Migration of Sakai content mired with issues that lead to course content to be misplaced, scrambled or not migrated at all. | Investigate alternative methods for migration: Work with Unizin/BTAA/Instructure on a migration tool Engage and work with an experienced migration vendor service Hire additional instructional designers to handle lengthy (5-40 hours/course) white-glove migration
Guidelines on course provisioning | Related to guidelines on LMS use, uncontrolled provisioning may lead to unintended uses | Task committee to recommend guidelines Scheduling/Registration generated On-Demand User-Requested

## Slide 18: Outstanding Decisions
Decision | Impact | Recommendation
Need of guidelines on use of LMS for non-academic scenarios | The need of established guidelines on the use of LMS for non-academic student use cases (demographically based sites, student groups, etc.)​ could negatively impact the student experience The need of guidelines creates risks around what new solutions will or won't be needed for non-instructional project sites. | Guidelines to be developed by working teams and should be recommended by the SC and be submitted for policy development. Guidelines should be developed around “use cases” such as academic courses, user training, student-oriented administrative sites, student groups, etc. to ensure all potential uses are covered under future policy. Cutover dates for Legacy LMS project sites and current Canvas project sites dates need to align with AUP effect
Solution for “Project” sites – Migrate to Canvas, then grandfather or migrate to new solution? | Approx 25,000 project sites have no transition solution. Many are actively being used | Based on Peer Institution Feedback, do not allow transition of these sites to Canvas. An alternate solution should be developed.