## Slide 1: Learning Management Systems
Transition to Canvas
Steering Committee
February 7, 2020

## Slide 2: Agenda
Migration Update
K-16 Solutions (Migration Tool and Updated Process)
LMS Technical Updates
Recommendations for Learning Technology Ecosystem
Next Steps

## Slide 3: Course Inventory by LMS
Chart: Fall Semester - 2019
| Blackboard (17%) | Canvas (48%) | eCollege (0%) | Moodle (3%) | Sakai (32%)
% of Courses | 0.17 | 0.48 | 0 | 0.03 | 0.32
Chart: Academic Year - 2018
| Blackboard (16%) | Canvas (26%) | eCollege (2%) | Moodle (8%) | Sakai (48%)
% of Courses | 0.16 | 0.26 | 0.02 | 0.08 | 0.48

## Slide 4: LMS Transition to Canvas
 | Spring | Fall | Summer | Winter | Grand Total
2018 | 8458 | 9516 | 1936 | 176 | 20086
BLACKBOARD | 1726 | 1879 | 405 | 41 | 4051
CANVAS | 1632 | 1882 | 666 | 39 | 4219
ECOLLEGE | 77 | 0 | 0 | 14 | 91
SAKAI | 5181 | 5755 | 957 | 82 | 11975
MOODLE | 637 | 244 | 312 | 0 | 1193
2019 | 10712 | 11955 | 2392 | 173 | 25232
BLACKBOARD | 1817 | 1977 | 391 | 36 | 4221
CANVAS | 2911 | 5757 | 1107 | 62 | 9837
SAKAI | 4887 | 3890 | 741 | 75 | 9593
MOODLE | 1097 | 331 | 153 | 0 | 1581

## Slide 5: LMS Transition to Canvas
 | Spring | Fall | Summer | Winter | Grand Total
2018 | 8458 | 9516 | 1936 | 176 | 20086
BLACKBOARD | 1726 | 1879 | 405 | 41 | 4051
CANVAS | 1632 | 1882 | 666 | 39 | 4219
ECOLLEGE | 77 | 0 | 0 | 14 | 91
SAKAI | 5181 | 5755 | 957 | 82 | 11975
MOODLE | 637 | 244 | 312 | 0 | 1193
2019 | 10712 | 11955 | 2392 | 173 | 25232
BLACKBOARD | 1817 | 1977 | 391 | 36 | 4221
CANVAS | 2911 | 5757 | 1107 | 62 | 9837
SAKAI | 4887 | 3890 | 741 | 75 | 9593
MOODLE | 1097 | 331 | 153 | 0 | 1581

## Slide 6: Moodle Migration Status
All RBHS courses being taught on Canvas for Spring 2020
All remaining Moodle courses to be migrated for Fall 2020
Project sites moved to alternative solutions*
Moodle System will enter a read-only state in May 2020
Student/course data will be preserved in Moodle for 5 years
* Includes Canvas as an alternative solution

## Slide 7: Sakai Migration Status
Target Migrations for Summer/Fall 2020
23 schools with fewer than 100 fall courses (700 total)
4 schools with more than 100 fall courses (900 total)
Camden has 574 courses (Camden is facilitating their own migration)
SAS has a total of 2112 fall courses, will need to be broken down based on capacity

## Slide 8: Blackboard Migration Status
Law School – All Spring 2020 LS-N courses taught in Canvas
  LS-N course migrations for Fall 2020 to be completed by May 2020
Rutgers Business School –courses being migrated for Fall 2020
  RBS has both Blackboard and Sakai courses
  K-16 will be available to provide migration services for both Blackboard and Sakai RBS courses.
Canvas support for RU-N faculty and students will be facilitated by TLT.

## Slide 9: K-16 Solutions Migration Tool
K-16 completed development of an automated migration tool
Tool is first and only migration tool available for Sakai 11
Tool improves migration process by:
  Process automation and bulk migration
  Alleviates pain points
  Produces exception report
The agreement will allow up to 21,000 Sakai migrations and 10,000 from Blackboard
The migration will be completed within a 2-year time frame

## Slide 10: Migration Process Update (Manual Migration)
Unit Contact
Course Inventory Identified
Manual Migration
ID Review
Instructor Training/Support
Course Approval
Course Archive Developed

## Slide 11: Migration Process Update (K-16 Migration)
Unit Contact
Course Inventory Identified
Bulk Migration
(K-16)
Course Shell Available with Exception Report
Instructor Training
On-demand ID services
Course Approval
Course Archive Developed

## Slide 12: LMS Technical Updates
REGIS GradeSync – Spring 2020
NetID Lookup in Canvas – Spring 2020
Photo Rosters in Canvas – Fall 2020
New Faculty Tools Portal in Canvas for local tools/apps
Sub-Account Admin and API - access request process implemented Spring 2020 term using OIT-EAS policies
LMS Usage Dashboard
  https://canvas.rutgers.edu/transition/lms-usage-statistics/

## Slide 13: Recommendations for Learning Technology Ecosystem
Recommendations or areas of improvement collected via:
  LMS Transition Steering Committee Discussions
  LMS Transition Working Groups
  ID/ITS Meetings
  Unit Migration Meetings
  Faculty Training
  Project Team Discussions
The LMS Transition Steering Committee will begin to document formal recommendations for improvements to the Rutgers Learning Technology Ecosystem

## Slide 14: Recommendations to be Discussed
Learning Technology Ecosystem Oversight/Shared Governance
  U-wide Initiatives, Tool Consolidations, Future Transitions
  Research/Awareness of Learning Technology Trends in Higher Education
  Development and enforcement of appropriate use guidelines
Standard Processes for Selecting, Piloting, Purchasing, and Implementing new Learning Technologies
Clear and Defined LT Support Structure (U-wide, Campus, Local)
  Increased Local Control in the LT Ecosystem
Learning Technology Compliance
  Data Security/Retention
  HIPPA, FERPA, ADA

## Slide 15: Recommendations to be Discussed (cont.)
Improved Integration between Physical/Digital Learning Technology
Facilitate Collaboration between University and Consortiums
Improved Communication between University Community and Learning Technology Professionals
Standardization of pedagogical, development, and review processes
Learning Analytics Oversight and Guidance (UDP, etc.)
Provide Oversight of Learning Technology Operations
  Local/custom Development
  Third Party Integrations
  Provisioning Processes

## Slide 16: Next Steps
Finalize agreement with K-16 solutions for Sakai to Canvas migration tool/services
Develop and verify new migration process
Develop new migration schedule and communicate with academic unit leadership
Continue LMS technical developments
Continue development of learning technology recommendations

## Slide 17: Appendix

## Slide 18: Key Project Risks and Issues
Risk / Issue | Impact | Plan
Need of guidelines on use of LMS for non-academic scenarios | The need of established guidelines on the use of LMS for non-academic student use cases (demographically based sites, student groups, etc.)​ could negatively impact the student experience The need of guidelines creates risks around what new solutions will or won't be needed for non-instructional project sites. | Establish a Committee comprised of Faculty, Staff, Stakeholders and IT to develop guidelines and policies on the use of LMS
Need of Project Sites Solution | Approx 25,000 project sites are on Sakai. | Users can continue to utilize legacy LMSs for non-academic use until further notice. A use case matrix is in development to identify solutions for projects sites. Steering Committee and Project Teams will work to fill gaps via development or procurement of new solutions.
A streamlined help desk support model would improve customer experience. | Current help desk process is a direct handoff from OIT help desk to the LMS help desk | A coordinated optimization effort should be initiated with the Rutgers Service Management Office and the two help desks.

## Slide 19: Key Project Risks and Issues
Risk / Issue | Impact | Plan
Sakai GradeBook passback functionality to Rutgers SIS is not available in Canvas | The lack of GradeBook passback functionality in Canvas would require a manual workaround | A development effort has been identified to provide the necessary functionality in Canvas, however, target date for completion is 4Q19. Thus Sakai migrations will be deferred until available.
Sakai migration pathways are typically inefficient | Migration of Sakai content mired with issues that lead to course content to be misplaced, scrambled or not migrated at all. | Investigate alternative methods for migration: Work with Unizin/BTAA/Instructure on a migration tool Engage and work with an experienced migration vendor service Hire additional instructional designers to handle lengthy (5-40 hours/course) white-glove migration
Guidelines on course provisioning | Related to guidelines on LMS use, uncontrolled provisioning may lead to unintended uses | Task committee to recommend guidelines Scheduling/Registration generated On-Demand User-Requested

## Slide 20: Outstanding Decisions
Decision | Impact | Recommendation
Need of guidelines on use of LMS for non-academic scenarios | The need of established guidelines on the use of LMS for non-academic student use cases (demographically based sites, student groups, etc.)​ could negatively impact the student experience The need of guidelines creates risks around what new solutions will or won't be needed for non-instructional project sites. | Guidelines to be developed by working teams and should be recommended by the SC and be submitted for policy development. Guidelines should be developed around “use cases” such as academic courses, user training, student-oriented administrative sites, student groups, etc. to ensure all potential uses are covered under future policy. Cutover dates for Legacy LMS project sites and current Canvas project sites dates need to align with AUP effect
Solution for “Project” sites – Migrate to Canvas, then grandfather or migrate to new solution? | Approx 25,000 project sites have no transition solution. Many are actively being used | Based on Peer Institution Feedback, do not allow transition of these sites to Canvas. An alternate solution should be developed.