## Slide 1: Learning Management Systems
Transition to Canvas
Steering Committee
March 4, 2020

## Slide 2: Agenda
Discuss & approve new migration process (K-16 Solution)
Migration next steps
Discuss and approve migration plan/timeline
LMS technical updates
Recommendations for Learning Technology Ecosystem
  Learning Technology Leadership Team
Next steps

## Slide 3: K-16 Solutions Migration Tool
K-16 completed development of an automated migration tool
Tool is first and only migration tool available for Sakai 11
Tool improves migration process by:
  Process automation and bulk migration
  Alleviates pain points
  Produces exception report
The agreement will allow up to 21,000 Sakai migrations and 10,000 from Blackboard
The migration will be completed within a 2-year time frame

## Slide 4: Migration Process Update (Manual Migration)
Unit Contact
Course Inventory Identified
Manual Migration
ID Review
Instructor Training/Support
Course Approval
Course Archive Developed

## Slide 5: Migration Process Update (K-16 Migration)
Unit Contact
Course Inventory Identified
Bulk Migration
(K-16)
Course Shell Available with Exception Report
Instructor Training
On-demand ID services
Course Approval
Course Archive Developed

## Slide 6: Proposed Migration Plan/Timeline
Mar-20 | Apr-20 | May-20 | Jun-20 | Jul-20 | Aug-20 | Sep-20 | Oct-20 | Nov-20 | Dec-20 | Jan-21 | Feb-21 | Mar-21 | Apr-21 | May-21 | Jun-21 | Jul-21 | Aug-21 | Sep-21 | Oct-21 | Nov-21 | Dec-21 | Jan-22 | Feb-22 | Mar-22
Fall 2020 - ~1800
RBS, LSN,
GSN
SCJ, SPAA
SCI, BSP, EMSP
GSAPP, GSE
MGSA, OP, SOE
SMLR
Spring 2021 - ~2520
RBS
GSN, SASN
SCJ, SPAA
BSP, EMSP
GSAPP, GSE
MGSA, OP, SOE
SMLR
SEBS, SSW
SAS
Fall 2021 - TBD
SASN
SEBS, SSW
SAS
Spring 2022 - TBD
SAS
Blackboard - SAS course breakdown is TBD – Contract Constraint 720 Days -

## Slide 7: Migration Next Steps
Develop migration pathways between K-16 and LMS
Begin bulk Blackboard migrations for RBS
Finalize and verify accuracy of migration exception reports
Redesign training and resources to match process changes
Begin bulk Sakai migrations for RBS
Reach out to academic unit leadership to schedule migrations

## Slide 8: LMS Technical Updates
REGIS GradeSync – Spring 2020
NetID Lookup in Canvas – Spring 2020
Photo Rosters in Canvas – Fall 2020
New Faculty Tools Portal in Canvas for local tools/apps
Sub-Account Admin and API - access request process implemented Spring 2020 term using OIT-EAS policies
LMS Usage Dashboard
  https://canvas.rutgers.edu/transition/lms-usage-statistics/

## Slide 9: Recommendations for Learning Technology Ecosystem
Recommendations or areas of improvement collected via:
  LMS Transition Steering Committee Discussions
  LMS Transition Working Groups
  ID/ITS Meetings
  Unit Migration Meetings
  Faculty Training
  Project Team Discussions
The LMS Transition Steering Committee will begin to document formal recommendations for improvements to the Rutgers Learning Technology Ecosystem

## Slide 10: Recommendations for Learning Technology Ecosystem
Project Sponsor’s Charge
  Governance & Policy
  Migration Support
  Properly Preserve Academic Intellectual Property
Improve the Overall Student Learning Experience
  Consolidation of LMS onto Canvas
  Further changes/actions required, but a permanent structure and processes are needed first

## Slide 11: Recommendations for Learning Technology Ecosystem
Gather Information
Internal discussions
Define Objectives
What can we recommend?
Draft & Review
Small working group to draft recommendations
Model comparisons
Survey peers
What should be left to the new governance group to develop?
LMS SC will review and provide feedback
Identify current gaps/opportunities/needs

## Slide 12: Recommendations to be Discussed
Learning Technology Ecosystem Oversight/Shared Governance
  U-wide Initiatives, Tool Consolidations, Future Transitions
  Research/Awareness of Learning Technology Trends in Higher Education
  Development and enforcement of appropriate use guidelines
Standard Processes for Selecting, Piloting, Purchasing, and Implementing new Learning Technologies
Clear and Defined LT Support Structure (U-wide, Campus, Local)
  Increased Local Control in the LT Ecosystem
Learning Technology Compliance
  Data Security/Retention
  HIPPA, FERPA, ADA

## Slide 13: Recommendations to be Discussed (cont.)
Improved Integration between Physical/Digital Learning Technology
Facilitate Collaboration between University and Consortiums
Improved Communication between University Community and Learning Technology Professionals
Standardization of pedagogical, development, and review processes
Learning Analytics Oversight and Guidance (UDP, etc.)
Provide Oversight of Learning Technology Operations
  Local/custom Development
  Third Party Integrations
  Provisioning Processes

## Slide 14: Learning Technology Governance/Oversight
“A set of governance committees and advisory groups exists to prioritize shared needs regarding teaching and learning with technology at NYU.”
“The Teaching & Transformational Learning Technologies Committee (TTLTC) provides input for the teaching and learning mission of Texas A&M University by reviewing, evaluating and recommending strategies, plans and policies regarding IT projects and services that support teaching and learning by faculty and students.”

## Slide 15: Learning Technology Governance/Oversight
”The Academic Technology Governance Council (ATC) was created to ensure that technology services are more effectively aligned throughout the University and to enable the faculty and academic areas to participate directly in providing strategic direction in technology decision-making for campus.
“The committee consults on technology issues impacting teaching, learning, advising, and student life and makes recommendations on the implementation and continuing evolution of various academic technology services.”

## Slide 16: Learning Technology Governance/Oversight
Learning Technology Leadership Team
Operations Committee
User Advisory Groups (Faculty, Students, ITS)
LT Support Coordination
Innovation & Advancement
Notes: Common Names:
Learning Technology Leadership Team
Teaching & Learning with Technology Committee
Academic Technology Council

## Slide 17: Learning Technology Governance/Oversight
LTLT
CIO
Faculty
Academic Leaders
LT Leaders
IT Leaders
Student Representatives

## Slide 18: Learning Technology Governance/Oversight
LTLT Guiding Principles
  Teaching and learning should be enhanced through the use of technology, not encumbered by it. I.e. a student’s learning comes first, technology second.
  Overall technology costs to students should be minimized.
  Faculty to play a key role in use of and choices of educational technology.
  Technology should support student success.

## Slide 19: Learning Technology Governance/Oversight
LTLT Charges
  Provides strategic leadership for the Learning Technology Ecosystem in order to support the teaching and learning mission.
  Makes recommendations/decisions on LT investments.
  Provides strategic guidance for identification, selection and adoption of significant University-wide learning technologies.
  Oversees the development of policies regarding the deployment, use and operation of learning technologies, in collaboration with other relevant academic committees.

## Slide 20: Next Steps
Develop and verify new migration process (K-16)
Finalize and communicate transition timeline/migration plan
Meet with academic leadership to begin unit migrations
Continue LMS technical developments
Continue development of learning technology recommendations

## Slide 21: Appendix

## Slide 22: Key Project Risks and Issues
Risk / Issue | Impact | Plan
Need of guidelines on use of LMS for non-academic scenarios | The need of established guidelines on the use of LMS for non-academic student use cases (demographically based sites, student groups, etc.)​ could negatively impact the student experience The need of guidelines creates risks around what new solutions will or won't be needed for non-instructional project sites. | Establish a Committee comprised of Faculty, Staff, Stakeholders and IT to develop guidelines and policies on the use of LMS
Need of Project Sites Solution | Approx 25,000 project sites are on Sakai. | Users can continue to utilize legacy LMSs for non-academic use until further notice. A use case matrix is in development to identify solutions for projects sites. Steering Committee and Project Teams will work to fill gaps via development or procurement of new solutions.
A streamlined help desk support model would improve customer experience. | Current help desk process is a direct handoff from OIT help desk to the LMS help desk | A coordinated optimization effort should be initiated with the Rutgers Service Management Office and the two help desks.

## Slide 23: Key Project Risks and Issues
Risk / Issue | Impact | Plan
Sakai GradeBook passback functionality to Rutgers SIS is not available in Canvas | The lack of GradeBook passback functionality in Canvas would require a manual workaround | A development effort has been identified to provide the necessary functionality in Canvas, however, target date for completion is 4Q19. Thus Sakai migrations will be deferred until available.
Sakai migration pathways are typically inefficient | Migration of Sakai content mired with issues that lead to course content to be misplaced, scrambled or not migrated at all. | Investigate alternative methods for migration: Work with Unizin/BTAA/Instructure on a migration tool Engage and work with an experienced migration vendor service Hire additional instructional designers to handle lengthy (5-40 hours/course) white-glove migration
Guidelines on course provisioning | Related to guidelines on LMS use, uncontrolled provisioning may lead to unintended uses | Task committee to recommend guidelines Scheduling/Registration generated On-Demand User-Requested

## Slide 24: Outstanding Decisions
Decision | Impact | Recommendation
Need of guidelines on use of LMS for non-academic scenarios | The need of established guidelines on the use of LMS for non-academic student use cases (demographically based sites, student groups, etc.)​ could negatively impact the student experience The need of guidelines creates risks around what new solutions will or won't be needed for non-instructional project sites. | Guidelines to be developed by working teams and should be recommended by the SC and be submitted for policy development. Guidelines should be developed around “use cases” such as academic courses, user training, student-oriented administrative sites, student groups, etc. to ensure all potential uses are covered under future policy. Cutover dates for Legacy LMS project sites and current Canvas project sites dates need to align with AUP effect
Solution for “Project” sites – Migrate to Canvas, then grandfather or migrate to new solution? | Approx 25,000 project sites have no transition solution. Many are actively being used | Based on Peer Institution Feedback, do not allow transition of these sites to Canvas. An alternate solution should be developed.