## Slide 1: LMS Transition to Canvas
Project Update
September 17th, 2020

## Slide 2: Agenda
Migration Updates
Updated Migration Plan/Timeline
Migration Process Updates
Technical Developments
Next Steps

## Slide 3: Blackboard Migration Updates
The Rutgers Business School is now teaching on Canvas.
RBS migrations to be fully completed after the Fall 20 term.

## Slide 4: Migration Plan/Timeline (as of July 2020)
Mar-20 | Apr-20 | May-20 | Jun-20 | Jul-20 | Aug-20 | Sep-20 | Oct-20 | Nov-20 | Dec-20 | Jan-21 | Feb-21 | Mar-21 | Apr-21 | May-21 | Jun-21 | Jul-21 | Aug-21 | Sep-21 | Oct-21 | Nov-21 | Dec-21 | Jan-22 | Feb-22 | Mar-22
Fall 2020
RBS
LSN
SCI
MGSA
SOE
SMLR
BSP
Spring 2021
MGSA
SOE
SMLR
SEBS
SAS
EMSoP
Fall 2021
SAS
SSW
GSE
Project Sites
Spring 2022
SAS
Project Sites
GSAPP
RU - N
Completed/Underway (Teaching on Canvas begins Fall 2020)
Next Migrations (Teaching on Canvas begins Spring 2021)
Blackboard (Teaching on Canvas begins Spring 2021)

## Slide 5: Migration Process Improvements
Course Inventory: There is no longer an emphasis on each unit approving their course inventory
Automated migration tool (K-16) has expediated process
  Courses being migrated in bulk with limited exceptions
    Avg exceptions per course: 1, Max exceptions per course: 26
Automated bulk migrations have removed resource constraints
  Initial migrations will now include entire 2-year inventory
Individual instructor approval now optional

## Slide 6: LMS Technical Updates
REGIS GradeSync – Spring 2020
  Successfully launched for Spring, feedback has been positive
  V2 will include integration with RBHS/Banner
Photo Rosters in Canvas – Fall 2020
  On target
WebEx/Canvas integration – Fall 2020
  WebEx on target, Zoom integration currently under development
SRDB Provisioning – Spring 2021

## Slide 7: Next Steps
Complete migrations underway
Prepare unit migration plans for Spring 2021 and beyond
Continue development on the technical improvements
Continue optimization of LMS support network/services
Resume work around recommendations for improving the learning technology ecosystem

## Slide 8: Fall 2020 LMS Steering Committee Meetings
Next project update will be sent in early September
Meetings will be held virtually during the Fall 2020 semester
A Doodle poll will be sent out in late August to determine availability